## Sheet1
Project Delivery Schedule - R11414 Sydney Metro Airport
Shipment # | Container # | Container Size | RF167 Egg 7.8kN/mm (M2-167) | RF167 Egg 10kN/mm (M2-TBA) | RF167 Egg 12kN/mm (M2-TBA) | RF167 Egg 20kN/mm (M2-TBA) | Ss8 150mm Screwspike (M2-2110) | Dowels 135mm (M2-2302N) | Plastic Caps (M2-9013) | Fe6 Spring Washer (M2-2203) | HDPE 3mm Basepad (BP402) (M2-3007-3) | HDPE 5mm Rail Seat Pad (RP408) (M2-3710) | Rail Clip (M2-9001C) | Insulator (M2-9021C) | EXW DATE | ETD Port | Actual Departure Date | Shipping Line | VESSEL NAME / VOYAGE | BILL OF LADING NO. | ETA Sydney Port | Actual Arrival Sydney Port | CONTAINER NUMBER | Destination | ETA Site
SAMPLES | N/A | N/A | 2 |  |  |  | 4 | 8 | 8 | 4 | 2 | 0 | 0 | 0 | 2024-07-10 | 2024-07-16 | 2024-07-16 |  | DHL Air Courier | 4577566744 | 2024-07-16 | 2024-07-16 | N/A | MITTAGONG | TBA
SAMPLES | N/A | N/A | 0 |  |  |  | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-05 | N/A | 2024-08-05 |  | Ex Delkor | N/A | N/A | N/A | N/A | GRAFTON | 2024-08-06
1 | 1 | 20' |  |  |  |  | 24000 | 38400 | 0 | 32000 | 0 | 0 | 0 | 0 | 2024-08-18 | 2024-09-07 | 2024-09-07 |  | OOCL Brazil V.OAJHYS1NL | OOLU2151979390 | 2024-09-30 |  | CBHU4452090 | MITTAGONG | 2024-10-07
| 2 | 20' | 1260 | [5 empty] | 0 |  | 18000 | 0 | 0 | 0 | [8 empty] | FCIU5463517
2 | 3 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-09-03 | 2024-09-23 |  |  | OOCL CANADA 108S | OOLU2152350030 | 2024-10-10 |  | CSNU1067436 | MITTAGONG | 2024-10-17
| 4 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [8 empty] | SEGU2940889
3 | 5 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-09-13 | 2024-10-02 |  |  | CMA CGM FIORDLAND / 231S | SHA47987840 | 2024-10-25 |  | CBHU4384919 | MITTAGONG | 2024-11-01
| 6 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [8 empty] | CSLU1060141
4 | 7 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-09-28 | 2024-10-05 |  |  | OOCL BEIJING 114S | OOLU2152769370 | 2024-11-02 |  | CSNU1569753 | MITTAGONG | 2024-11-09
| 8 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [8 empty] | DFSU1329870
| 9 | 20' |  |  |  |  | 24000 | 38400 | 0 | 32000 |  | 0 | 0 | 0 | [8 empty] | CSNU1286460
5 | 10 | 20' | 120 |  |  |  | 0 | 4800 | 0 | 0 | 0 | 26000 | 13000 | 23944 | 2024-09-30 | 2024-10-17 |  |  | ANL GIPPSLAND V.078S | 24101062 | 2024-11-05 |  | HAKU0033590 | SITE | 2024-11-12
6 | 11 | 20' | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 13000 | 8000 | 2024-10-09 | 2024-10-19 |  |  | OOCL BRAZIL 24043S | OOLU2153147770 | 2024-11-15 |  | CSLU2236071 | SITE | 2024-11-22
| 12 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [8 empty] | FCIU5010953 | MITTAGONG
| 13 | 20' |  |  |  |  | 24000 | 38400 | 0 | 32000 |  | 0 | 0 | 0 | [8 empty] | OOLU1705163
| 14 | 20' | 1260 | [7 empty] | 18000 | 0 | 0 | 0 | [8 empty] | CBHU4336211
7 | 15 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-10-23 | 2024-11-04 |  |  | MSC REBECCA III V.KN443 | 24101100 | 2024-11-20 |  | MSMU2323945 | MITTAGONG | 2024-11-27
| 16 | 20' | 1692 | [8 empty] | 0 | 0 | 0 | [8 empty] | MSDU2797573
8 | 17 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-11-06 | 2024-11-23 |  |  |  |  | 2024-12-08 |  |  | MITTAGONG | 2024-12-15
| 18 | 20' | 1680 | [8 empty] | 0 | 0 | 0
9 | 19 | 20' | [10 empty] | 26000 | 24000 | 2024-11-10 | 2024-11-23 |  |  |  |  | 2024-12-05 |  |  | SITE | 2024-12-12
10 | 20 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-12-02 | 2024-12-17 |  |  |  |  | 2025-01-04 |  |  | MITTAGONG | 2025-01-11
| 21 | 20' |  |  |  |  | 24000 | 38400 | 0 | 31944 |  | 0 | 0 | 0
| 22 | 20' | 1680 | [8 empty] | 0 | 0 | 0
11 | 23 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-12-09 | 2024-12-20 |  |  | OOCL MIAMI | CMAU1804604 | 2025-01-04 |  |  | MITTAGONG | 2025-01-11
| 24 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [5 empty] | HJCU2119856
12 | 25 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-12-20 | 2024-12-28 |  |  | OOCL CANADA | OOLU1468760 | 2025-01-10 |  |  | MITTAGONG | 2025-01-17
| 26 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [5 empty] | TEMU3398172
13 | 27 | 20' | [9 empty] | 14000 | 26000 | 24000 | 2025-02-15 | 2025-02-27 |  |  |  |  | 2025-03-17 |  |  | SITE | 2025-03-24
14 | 28 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2025-01-10 | 2025-01-27 |  |  |  |  | 2025-02-15 |  |  | MITTAGONG | 2025-02-22
| 29 | 20' | 426 |  |  |  | 16000 | 38400 |  |  |  | 0 | 0 | 0
| 30 | 20' | 1680 | [8 empty] | 0 | 0 | 0
31
15 | 31 | 20' | 1260 | 0 | 0 | 0 |  |  |  |  | 18000 | 0 | 0 | 0 | 2025-03-11 | 2025-03-21 |  |  |  |  | 2025-04-06 |  |  | MITTAGONG | 2025-04-13
16 | 32 | 20' | 720 | 0 | 0 | 0 | 15944 | 38400 |  |  |  | 0 | 0 | 0 | 2025-03-24 | 2025-04-02 |  |  |  |  | 2025-04-18 |  |  | MITTAGONG | 2025-04-25
| 33 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | [9 empty] | MITTAGONG
| 34 | 20' |  | 0 | 0 | 0 | [5 empty] | 14000 | 26000 | 28000 | [9 empty] | SITE
17 | 35 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-03-28 | 2025-04-04 |  |  |  |  | 2025-04-19 |  |  | MITTAGONG | 2025-04-26
18 | 36 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-04-03 | 2025-04-11 |  |  |  |  | 2025-04-26 |  |  | MITTAGONG | 2025-05-03
| 37 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | [9 empty] | MITTAGONG
19 | 38 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-04-08 | 2025-04-15 |  |  |  |  | 2025-05-06 |  |  | MITTAGONG | 2025-05-13
20 | 39 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-04-15 | 2025-04-22 |  |  |  |  | 2025-05-13 |  |  | MITTAGONG | 2025-05-20
| 40 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | [9 empty] | MITTAGONG
21 | 41 |  | 1680 | [11 empty] | 2025-04-29 | 2025-05-06 |  |  |  |  | 2025-05-27 |  |  | MITTAGONG | 2025-06-03
| 42 | 20' | 1440 | 0 | 0 | 0 |  |  |  |  | 9972 | 0 | 0 | 0 | [9 empty] | MITTAGONG
| 43 | 20' | 1680 | 0 | 0 | 0 | [17 empty] | MITTAGONG
| 44 | 20' |  | 0 | 0 | 0 | [5 empty] | 9972 | 23944 | 20000 | [9 empty] | SITE
22 | 45 | 20' | 1680 | 0 | 0 | 0 | [8 empty] | 2025-05-13 | 2025-05-20 |  |  |  |  | 2025-06-10 |  |  | MITTAGONG | 2025-06-17
| 46 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | [9 empty] | MITTAGONG
23 | 47 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-05-27 | 2025-06-03 |  |  |  |  | 2025-06-24 |  |  | MITTAGONG | 2025-07-01
| 48 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | [9 empty] | MITTAGONG
24 | 49 | 20' | 650 | 1034 |  | 0 | [5 empty] | 0 | 0 | 0 | 2025-06-03 | 2025-06-10 |  |  |  |  | 2025-07-01 |  |  | MITTAGONG | 2025-07-08
| 50 | 20' |  |  | 256 | 1004 |  | 28800 |  |  |  | 0 | 0 | 0 | [9 empty] | MITTAGONG
25 | 51 | 20' |  |  | 0 | 1680 | [5 empty] | 0 | 0 | 0 | 2025-06-13 | 2025-06-20 |  |  |  |  | 2025-07-11 |  |  | MITTAGONG | 2025-07-18
| 52 | 20' | 0 |  |  | 1080 | 8468 | 8824 |  | 8468 | 4234 | 0 | 0 | 0 | [9 empty] | MITTAGONG
26 | 53 | 20' |  | 0 | 0 | 1680 | [5 empty] | 0 | 0 | 0 | 2025-06-19 | 2025-06-26 |  |  |  |  | 2025-07-17 |  |  | MITTAGONG | 2025-07-24
| 54 | 20' | 0 | 0 | 0 | 564 | [5 empty] | 4234 | 8468 | 8468 | [9 empty] | MITTAGONG/SITE
ORDER TOTALS |  |  | 62204 | 1056 | 294 | 6258 | 139624 | 279248 | 139624 | 139624 | 69812 | 69812 | 139624 | 139624
DELIVERY TOTALS |  |  | 60908 | 1034 | 256 | 6008 | 136412 | 272824 | 0 | 136412 | 68206 | 68206 | 136412 | 136412
|  |  | -1296 | -22 | -38 | -250 | -3212 | -6424 | -139624 | -3212 | -1606 | -1606 | -3212 | -3212 | 0
| 9230Rev1 | 9280Rev1
Ss8 x 150mm | 48000 | 88412 | 136412
Nylon Dowel 135mm | 76800 | 196024 | 272824
HDPE Base Pad | 18000 | 50206 | 68206
Formulas:
ETA Site = +[ETA Sydney Port]+7
ETA Site = [ETA Sydney Port]+7
ETD Port = [EXW DATE]+7
ETA Sydney Port = [ETD Port]+18
EXW DATE = [EXW DATE, row above]+7