## Master Schedule Updated
Project Delivery Schedule - R11414 Sydney Metro Airport
Shipment # | Container # | Container Size | RF167 Egg 7.8kN/mm (M2-167) | RF167 Egg 10kN/mm (M2-TBA) | RF167 Egg 12kN/mm (M2-TBA) | RF167 Egg 20kN/mm (M2-TBA) | Ss8 150mm Screwspike (M2-2110) | Dowels 135mm (M2-2302N) | Plastic Caps (M2-9013) | Fe6 Spring Washer (M2-2203) | HDPE 3mm Basepad (BP402) (M2-3007-3) | HDPE 5mm Rail Seat Pad (RP408) (M2-3710) | Rail Clip (M2-9001C) | Insulator (M2-9021C) | EXW DATE | ETD Port | Actual Departure Date | Shipping Line | VESSEL NAME / VOYAGE | BILL OF LADING NO. | ETA Sydney Port | Actual Arrival Sydney Port | CONTAINER NUMBER | Destination | ETA Site
SAMPLES | N/A | N/A | 2 |  |  |  | 4 | 8 | 8 | 4 | 2 | 0 | 0 | 0 | 2024-07-10 | 2024-07-16 | 2024-07-16 |  | DHL Air Courier | 4577566744 | 2024-07-16 | 2024-07-16 | N/A | MITTAGONG | TBA
SAMPLES | N/A | N/A | 0 |  |  |  | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-05 | N/A | 2024-08-05 |  | Ex Delkor | N/A | N/A | N/A | N/A | GRAFTON | 2024-08-06
1 | 1 | 20' |  |  |  |  | 24000 | 38400 | 0 | 32000 | 0 | 0 | 0 | 0 | 2024-08-18 | 2024-09-07 | 2024-09-07 |  | OOCL Brazil V.OAJHYS1NL | OOLU2151979390 | 2024-09-30 |  | CBHU4452090 | MITTAGONG | 2024-10-07
| 2 | 20' | 1260 | [5 empty] | 0 |  | 18000 | 0 | 0 | 0 | [8 empty] | FCIU5463517
2 | 3 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-09-03 | 2024-09-23 |  |  | OOCL CANADA 108S | OOLU2152350030 | 2024-10-10 |  | CSNU1067436 | MITTAGONG | 2024-10-17
| 4 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [8 empty] | SEGU2940889
3 | 5 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-09-13 | 2024-10-02 |  |  | CMA CGM FIORDLAND / 231S | SHA47987840 | 2024-10-25 |  | CBHU4384919 | MITTAGONG | 2024-11-01
| 6 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [8 empty] | CSLU1060141
4 | 7 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-09-28 | 2024-10-05 |  |  | OOCL BEIJING 114S | OOLU2152769370 | 2024-11-02 |  | CSNU1569753 | MITTAGONG | 2024-11-09
| 8 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [8 empty] | DFSU1329870
| 9 | 20' |  |  |  |  | 24000 | 38400 | 0 | 32000 |  | 0 | 0 | 0 | [8 empty] | CSNU1286460
5 | 10 | 20' | 120 |  |  |  | 0 | 4800 | 0 | 0 | 0 | 26000 | 13000 | 23944 | 2024-09-30 | 2024-10-17 |  |  | ANL GIPPSLAND V.078S | 24101062 | 2024-11-05 |  | HAKU0033590 | SITE | 2024-11-12
6 | 11 | 20' | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 13000 | 8000 | 2024-10-09 | 2024-10-19 |  |  | OOCL BRAZIL 24043S | OOLU2153147770 | 2024-11-15 |  | CSLU2236071 | SITE | 2024-11-22
| 12 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [8 empty] | FCIU5010953 | MITTAGONG
| 13 | 20' |  |  |  |  | 24000 | 38400 | 0 | 32000 |  | 0 | 0 | 0 | [8 empty] | OOLU1705163
| 14 | 20' | 1260 | [7 empty] | 18000 | 0 | 0 | 0 | [8 empty] | CBHU4336211
7 | 15 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-10-23 | 2024-11-04 |  |  | MSC REBECCA III V.KN443 | 24101100 | 2024-11-20 |  | MSMU2323945 | MITTAGONG | 2024-11-27
| 16 | 20' | 1692 | [8 empty] | 0 | 0 | 0 | [8 empty] | MSDU2797573
8 | 17 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-11-06 | 2024-11-23 |  |  |  |  | 2024-12-08 |  |  | MITTAGONG | 2024-12-15
| 18 | 20' | 1680 | [8 empty] | 0 | 0 | 0
9 | 19 | 20' | [10 empty] | 26000 | 24000 | 2024-11-10 | 2024-11-23 |  |  |  |  | 2024-12-05 |  |  | SITE | 2024-12-12
10 | 20 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-12-02 | 2024-12-17 |  |  |  |  | 2025-01-04 |  |  | MITTAGONG | 2025-01-11
| 21 | 20' |  |  |  |  | 24000 | 38400 | 0 | 31944 |  | 0 | 0 | 0
| 22 | 20' | 1680 | [8 empty] | 0 | 0 | 0
11 | 23 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-12-09 | 2024-12-20 |  |  | OOCL MIAMI | CMAU1804604 | 2025-01-04 |  |  | MITTAGONG | 2025-01-11
| 24 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [5 empty] | HJCU2119856
12 | 25 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2024-12-20 | 2024-12-28 |  |  | OOCL CANADA | OOLU1468760 | 2025-01-10 |  |  | MITTAGONG | 2025-01-17
| 26 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | [5 empty] | TEMU3398172
13 | 27 | 20' | [9 empty] | 14000 | 26000 | 24000 | 2025-02-15 | 2025-02-22 |  |  |  |  | 2025-03-15 |  |  | SITE | 2025-03-22
14 | 28 | 20' | 1680 | [8 empty] | 0 | 0 | 0 | 2025-01-10 | 2025-01-27 |  |  |  |  | 2025-02-15 |  |  | MITTAGONG | 2025-02-22
| 29 | 20' | 426 |  |  |  | 16000 | 38400 |  |  |  | 0 | 0 | 0
| 30 | 20' | 1680 | [8 empty] | 0 | 0 | 0
31
15 | 32 | 20' | 1260 | 0 | 0 | 0 |  |  |  |  | 18000 | 0 | 0 | 0 | 2025-03-11 | 2025-03-18 |  |  |  |  | 2025-04-08 |  |  | MITTAGONG | 2025-04-15
16 | 33 | 20' | 720 | 0 | 0 | 0 | 15944 | 38400 |  |  |  | 0 | 0 | 0 | 2025-03-18 | 2025-03-25 |  |  |  |  | 2025-04-15 |  |  | MITTAGONG | 2025-04-22
| 34 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | [9 empty] | MITTAGONG
| 35 | 20' |  | 0 | 0 | 0 | [5 empty] | 14000 | 26000 | 28000 | [9 empty] | SITE
17 | 36 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-03-24 | 2025-03-31 |  |  |  |  | 2025-04-21 |  |  | MITTAGONG | 2025-04-28
18 | 37 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-04-01 | 2025-04-08 |  |  |  |  | 2025-04-29 |  |  | MITTAGONG | 2025-05-06
| 38 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | [9 empty] | MITTAGONG
19 | 39 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-04-07 | 2025-04-14 |  |  |  |  | 2025-05-05 |  |  | MITTAGONG | 2025-05-12
20 | 40 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-04-15 | 2025-04-22 |  |  |  |  | 2025-05-13 |  |  | MITTAGONG | 2025-05-20
| 41 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | [9 empty] | MITTAGONG
21 | 42 |  | 1680 | [11 empty] | 2025-04-21 | 2025-04-28 |  |  |  |  | 2025-05-19 |  |  | MITTAGONG | 2025-05-26
22 | 43 | 20' | 1440 | 0 | 0 | 0 |  |  |  |  | 9972 | 0 | 0 | 0 | 2025-04-29 | 2025-05-06 |  |  |  |  | 2025-05-27 |  |  | MITTAGONG | 2025-06-03
| 44 | 20' | 1680 | 0 | 0 | 0 | [17 empty] | MITTAGONG
| 45 | 20' |  | 0 | 0 | 0 | [5 empty] | 9972 | 23944 | 20000 | [9 empty] | SITE
23 | 46 | 20' | 1680 | 0 | 0 | 0 | [8 empty] | 2025-05-13 | 2025-05-20 |  |  |  |  | 2025-06-10 |  |  | MITTAGONG | 2025-06-17
| 47 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | [9 empty] | MITTAGONG
24 | 48 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-05-19 | 2025-05-26 |  |  |  |  | 2025-06-16 |  |  | MITTAGONG | 2025-06-23
25 | 49 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 2025-05-27 | 2025-06-03 |  |  |  |  | 2025-06-24 |  |  | MITTAGONG | 2025-07-01
| 50 | 20' | 1680 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | [9 empty] | MITTAGONG
26 | 51 | 20' | 266 | 700 | 294 | 0 |  | 20688 |  |  |  | 0 | 0 | 0 | 2025-06-02 | 2025-06-09 |  |  |  |  | 2025-06-30 |  |  | MITTAGONG | 2025-07-07
27 | 52 | 20' |  | 356 | 0 | 1324 | [5 empty] | 0 | 0 | 0 | 2025-06-12 | 2025-06-19 |  |  |  |  | 2025-07-10 |  |  | MITTAGONG | 2025-07-17
| 53 | 20' | 0 |  |  | 660 | 11680 | 23360 |  | 11680 | 5840 | 0 | 0 | 0 | [9 empty] | MITTAGONG
| 54 | 20' | 0 | 0 | 0 | 914 | [5 empty] | 5840 | 11680 | 11680 | [9 empty] | SITE
28 | 55 | 20' | 0 | 0 | 0 | 1680 | [8 empty] | 2025-06-19 | 2025-06-26 |  |  |  |  | 2025-07-17 |  |  | MITTAGONG | 2025-07-24
| 56 | 20' | 0 | 0 | 0 | 1680 | [17 empty] | MITTAGONG
ORDER TOTALS |  |  | 62204 | 1056 | 294 | 6258 | 139624 | 279248 | 139624 | 139624 | 69812 | 69812 | 139624 | 139624
DELIVERY TOTALS |  |  | 62204 | 1056 | 294 | 6258 | 139624 | 279248 | 0 | 139624 | 69812 | 69812 | 139624 | 139624
|  |  | 69812 |  |  |  | 0 | 0 | -139624 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
ETA Site = +[ETA Sydney Port]+7
ETA Site = [ETA Sydney Port]+7
ETD Port = [EXW DATE]+7
ETA Sydney Port = [ETD Port]+18

## TMT Schedule Updated
| 日产能 | 累计数 | Shipped |  | Balance | ETA | Customer Consumption | Balance | RF167 Egg 7.8kN/mm (M2-167) | Ss8 150mm Screwspike (M2-2110) | Dowels 135mm (M2-2302N) | Plastic Caps (M2-9013) | Fe6 Spring Washer (M2-2203) | HDPE 3mm Basepad (BP402) (M2-3007-3) | HDPE 5mm Rail Seat Pad (RP408) (M2-3710) | Rail Clip (M2-9001C) | Insulator (M2-9021C) |  | RF167 Egg 7.8kN/mm (M2-167) | Ss8 150mm Screwspike (M2-2110) | Dowels 135mm (M2-2302N) | Plastic Caps (M2-9013) | Fe6 Spring Washer (M2-2203) | HDPE 3mm Basepad (BP402) (M2-3007-3) | HDPE 5mm Rail Seat Pad (RP408) (M2-3710) | Rail Clip (M2-9001C) | Insulator (M2-9021C) | Balance | Ss8 150mm Screwspike (M2-2110) | Dowels 135mm (M2-2302N) | Plastic Caps (M2-9013) | Fe6 Spring Washer (M2-2203) | HDPE 3mm Basepad (BP402) (M2-3007-3) | HDPE 5mm Rail Seat Pad (RP408) (M2-3710) | Rail Clip (M2-9001C) | Insulator (M2-9021C)
2025-03-01 | 140 | 140 | [15 empty] | Basplate delivered | 34452 | 68904 | 137808 |  | 68904 | 34452 | 34452 | 68904 | 68904
2025-03-02 | 140 | 280 | [15 empty] | Baseplate in Stock | 546 | 1092 | 2184 |  | 1092 | 546 | 546 | 1092 | 1092
2025-03-03 | 140 | 420 | [15 empty] | Parts delivered |  | 96000 | 158400 |  | 127944 | 36000
2025-03-04 | 140 | 560 | [15 empty] | Parts in Stock |  | 16000 | 38400 |  |  |  | 26000 | 52000 | 55944
2025-03-05 | 140 | 700 | [15 empty] | Parts on the way | [6 empty] | 14000 | 26000 | 24000
2025-03-06 | 140 | 840 | [15 empty] | Balance |  | 42004 | 56808 |  | 57948 | 1002 | 5002 | 8004 | 9948
2025-03-07 | 140 | 980
2025-03-08 | 140 | 1120
2025-03-09 | 0 | 1120
2025-03-10 | 280 | 1400
2025-03-11 | 280 | 1680 | 1260 | 15 | 420 | 2025-04-15 | 1920 | -660 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840 | [6 empty] | 18000 |  |  |  |  | 38164 | 49128 | 0 | 54108 | 17082 | 3082 | 4164 | 6108
2025-03-12 | 280 | 1960 |  |  | 700 | 2025-04-16
2025-03-13 | 280 | 2240 |  |  | 980 | 2025-04-17
2025-03-14 | 280 | 2520 |  |  | 1260 | 2025-04-18
2025-03-15 | 280 | 2800 |  |  | 1540 | 2025-04-19
2025-03-16 | 0 | 2800 |  |  | 1540 | 2025-04-20
2025-03-17 | 420 | 3220 |  |  | 1960 | 2025-04-21
2025-03-18 | 420 | 3640 | 2400 | 16 | -20 | 2025-04-22 | 1920 | -180 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840 |  |  | 15944 | 38400 |  |  |  | 14000 | 26000 | 28000 |  | 50268 | 79848 | 0 | 50268 | 15162 | 15162 | 26324 | 30268
2025-03-19 | 420 | 4060 |  |  | 400 | 2025-04-23
2025-03-20 | 420 | 4480 |  |  | 820 | 2025-04-24
2025-03-21 | 420 | 4900 |  |  | 1240 | 2025-04-25
2025-03-22 | 420 | 5320 |  |  | 1660 | 2025-04-26
2025-03-23 | 0 | 5320 |  |  | 1660 | 2025-04-27
2025-03-24 | 420 | 5740 | 1680 | 17 | 400 | 2025-04-28
2025-03-25 | 420 | 6160 |  |  | 820 | 2025-04-29 | 1920 | -420 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-03-26 | 420 | 6580 |  |  | 1240 | 2025-04-30
2025-03-27 | 420 | 7000 |  |  | 1660 | 2025-05-01
2025-03-28 | 420 | 7420 |  |  | 2080 | 2025-05-02
2025-03-29 | 420 | 7840 |  |  | 2500 | 2025-05-03
2025-03-30 | 0 | 7840 |  |  | 2500 | 2025-05-04
2025-03-31 | 420 | 8260 |  |  | 2920 | 2025-05-05
2025-04-01 | 420 | 8680 | 3360 | 18 | -20 | 2025-05-06 | 1920 | 1020 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-04-02 | 420 | 9100 |  |  | 400 | 2025-05-07
2025-04-03 | 420 | 9520 |  |  | 820 | 2025-05-08
2025-04-04 | 420 | 9940 |  |  | 1240 | 2025-05-09
2025-04-05 | 420 | 10360 |  |  | 1660 | 2025-05-10
2025-04-06 | 0 | 10360 |  |  | 1660 | 2025-05-11
2025-04-07 | 420 | 10780 | 1680 | 19 | 400 | 2025-05-12
2025-04-08 | 420 | 11200 |  |  | 820 | 2025-05-13 | 1920 | 780 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-04-09 | 420 | 11620 |  |  | 1240 | 2025-05-14
2025-04-10 | 420 | 12040 |  |  | 1660 | 2025-05-15
2025-04-11 | 420 | 12460 |  |  | 2080 | 2025-05-16
2025-04-12 | 420 | 12880 |  |  | 2500 | 2025-05-17
2025-04-13 | 0 | 12880 |  |  | 2500 | 2025-05-18
2025-04-14 | 420 | 13300 |  |  | 2920 | 2025-05-19
2025-04-15 | 420 | 13720 | 3360 | 20 | -20 | 2025-05-20 | 1920 | 2220 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-04-16 | 420 | 14140 |  |  | 400 | 2025-05-21
2025-04-17 | 420 | 14560 |  |  | 820 | 2025-05-22
2025-04-18 | 420 | 14980 |  |  | 1240 | 2025-05-23
2025-04-19 | 420 | 15400 |  |  | 1660 | 2025-05-24
2025-04-20 | 0 | 15400 |  |  | 1660 | 2025-05-25
2025-04-21 | 420 | 15820 | 1680 | 21 | 400 | 2025-05-26
2025-04-22 | 420 | 16240 |  |  | 820 | 2025-05-27 | 1920 | 1980 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-04-23 | 420 | 16660 |  |  | 1240 | 2025-05-28
2025-04-24 | 420 | 17080 |  |  | 1660 | 2025-05-29
2025-04-25 | 420 | 17500 |  |  | 2080 | 2025-05-30
2025-04-26 | 420 | 17920 |  |  | 2500 | 2025-05-31
2025-04-27 | 0 | 17920 |  |  | 2500 | 2025-06-01
2025-04-28 | 420 | 18340 |  |  | 2920 | 2025-06-02
2025-04-29 | 420 | 18760 | 3120 | 22 | 220 | 2025-06-03 | 1920 | 3180 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840 | [6 empty] | 9972 | 9972 | 23944 | 20000 |  | 27228 | 33768 | 0 | 27228 | 13614 | 13614 | 27228 | 27228
2025-04-30 | 420 | 19180 |  |  | 640 | 2025-06-04
2025-05-01 | 0 | 19180 |  |  | 640 | 2025-06-05
2025-05-02 | 0 | 19180 |  |  | 640 | 2025-06-06
2025-05-03 | 0 | 19180 |  |  | 640 | 2025-06-07
2025-05-04 | 0 | 19180 |  |  | 640 | 2025-06-08
2025-05-05 | 0 | 19180 |  |  | 640 | 2025-06-09
2025-05-06 | 420 | 19600 |  |  | 1060 | 2025-06-10 | 1920 | 1260 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-05-07 | 420 | 20020 |  |  | 1480 | 2025-06-11
2025-05-08 | 420 | 20440 |  |  | 1900 | 2025-06-12
2025-05-09 | 420 | 20860 |  |  | 2320 | 2025-06-13
2025-05-10 | 420 | 21280 |  |  | 2740 | 2025-06-14
2025-05-11 | 0 | 21280 |  |  | 2740 | 2025-06-15
2025-05-12 | 420 | 21700 |  |  | 3160 | 2025-06-16
2025-05-13 | 420 | 22120 | 3360 | 23 | 220 | 2025-06-17 | 1920 | 2700 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-05-14 | 420 | 22540 |  |  | 640 | 2025-06-18
2025-05-15 | 420 | 22960 |  |  | 1060 | 2025-06-19
2025-05-16 | 420 | 23380 |  |  | 1480 | 2025-06-20
2025-05-17 | 420 | 23800 |  |  | 1900 | 2025-06-21
2025-05-18 | 0 | 23800 |  |  | 1900 | 2025-06-22
2025-05-19 | 420 | 24220 | 1680 | 24 | 640 | 2025-06-23
2025-05-20 | 420 | 24640 |  |  | 1060 | 2025-06-24 | 1920 | 2460 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-05-21 | 420 | 25060 |  |  | 1480 | 2025-06-25
2025-05-22 | 420 | 25480 |  |  | 1900 | 2025-06-26
2025-05-23 | 420 | 25900 |  |  | 2320 | 2025-06-27
2025-05-24 | 420 | 26320 |  |  | 2740 | 2025-06-28
2025-05-25 | 0 | 26320 |  |  | 2740 | 2025-06-29
2025-05-26 | 420 | 26740 |  |  | 3160 | 2025-06-30
2025-05-27 | 420 | 27160 | 3360 | 25 | 220 | 2025-07-01 | 1920 | 3900 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-05-28 | 46 | 27206 |  |  | 266 | 2025-07-02
2025-05-29 | 420 | 420 |  |  | 686 | 2025-07-03
2025-05-30 | 420 | 840 |  |  | 1106 | 2025-07-04
2025-05-31 | 216 | 1056 |  |  | 1322 | 2025-07-05
2025-06-01 |  |  |  |  | 1322 | 2025-07-06
2025-06-02 | 294 | 294 | 1260 | 26 | 356 | 2025-07-07
2025-06-03 | 420 | 420 |  |  | 776 | 2025-07-08 | 1920 | 3240 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840 |  |  |  | 20688 | [7 empty] | 8028 | 16056 | 0 | 8028 | 4014 | 4014 | 8028 | 8028
2025-06-04 | 420 | 840 |  |  | 1196 | 2025-07-09
2025-06-05 | 420 | 1260 |  |  | 1616 | 2025-07-10
2025-06-06 | 420 | 1680 |  |  | 2036 | 2025-07-11
2025-06-07 | 420 | 2100 |  |  | 2456 | 2025-07-12
2025-06-08 |  | 2100 |  |  | 2456 | 2025-07-13
2025-06-09 | 420 | 2520 |  |  | 2876 | 2025-07-14
2025-06-10 | 420 | 2940 |  |  | 3296 | 2025-07-15 | 1920 | 1320 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-06-11 | 420 | 3360 |  |  | 3716 | 2025-07-16
2025-06-12 | 420 | 3780 | 3254 | 27 | 882 | 2025-07-17
2025-06-13 | 420 | 4200 |  |  | 1302 | 2025-07-18
2025-06-14 | 420 | 4620 |  |  | 1722 | 2025-07-19
2025-06-15 |  | 4620 |  |  | 1722 | 2025-07-20
2025-06-16 | 420 | 5040 |  |  | 2142 | 2025-07-21
2025-06-17 | 420 | 5460 |  |  | 2562 | 2025-07-22 | 1920 | 2654 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840 |  |  | 11680 | 23360 |  | 11680 | 5840 | 5840 | 11680 | 11680 |  | 12028 | 24056 | 0 | 12028 | 6014 | 6014 | 12028 | 12028
2025-06-18 | 420 | 5880 |  |  | 2982 | 2025-07-23
2025-06-19 | 378 | 6258 | 3360 | 28 | 0 | 2025-07-24
2025-06-20 | [5 empty] | 2025-07-25
2025-06-21 | [5 empty] | 2025-07-26
2025-06-22 | [5 empty] | 2025-07-27
2025-06-23 | [5 empty] | 2025-07-28
2025-06-24 | [5 empty] | 2025-07-29 | 1920 | 4094 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-06-25 | [5 empty] | 2025-07-30
2025-06-26 | [5 empty] | 2025-07-31
2025-06-27 | [5 empty] | 2025-08-01
2025-06-28 | [5 empty] | 2025-08-02
2025-06-29 | [5 empty] | 2025-08-03
2025-06-30 | [5 empty] | 2025-08-04
2025-07-01 | [5 empty] | 2025-08-05 | 1920 | 2174 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-07-02 | [5 empty] | 2025-08-06
2025-07-03 | [5 empty] | 2025-08-07
2025-07-04 | [5 empty] | 2025-08-08
2025-07-05 | [5 empty] | 2025-08-09
2025-07-06 | [5 empty] | 2025-08-10
2025-07-07 | [5 empty] | 2025-08-11
2025-07-08 | [5 empty] | 2025-08-12 | 1920 | 254 |  | 3840 | 7680 |  | 3840 | 1920 | 1920 | 3840 | 3840
2025-07-09 | [5 empty] | 2025-08-13
2025-07-10 | [5 empty] | 2025-08-14
2025-07-11 | [5 empty] | 2025-08-15
2025-07-12 | [5 empty] | 2025-08-16
2025-07-13 | [5 empty] | 2025-08-17
2025-07-14 | [5 empty] | 2025-08-18
2025-07-15 | [5 empty] | 2025-08-19 | 254 | 0 |  | 508 | 1016 |  | 508 | 254 | 254 | 508 | 508 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 34814 | 34814 |  |  |  | 34814 |  |  | 69628 | 139256 | 0 | 69628 | 34814 | 34814 | 69628 | 69628 |  |  | 69628 | 139256 | 0 | 69628 | 34814 | 34814 | 69628 | 69628
10kN
15kN
20kN

## Container Updated
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 63972 | 1066.2 | 967043.4 | 823.7395 | TO MITTAGONG | 0
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 | 127944 | 127.944 | 78045.84 | 61.9249 | TO MITTAGONG | 0
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 | 63972 | 21.324 | 20044.56 | 28.1057 | TO MITTAGONG | 0
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 | 63972 | 7.4386 | 6055.0242 | 9.1464 | TO SITE | 0
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 255888 | 53.31 | 25162.32 | 68.3461 | TO MITTAGONG | -57000
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 | 127944 | 31.986 | 7132.878 | 19.3955 | TO SITE | 0
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 | 127944 | 127.944 | 106193.52 | 91.6488 | TO SITE | 0
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 | 127944 | 31.986 | 13562.064 | 15.4812 | TO MITTAGONG | 0
[11 empty] | TTL | 959580 | 1468.1326 | 1223239.6062 | 1117.7881
#1 | 20GP | TO MITTAGONG | FOSCO |  | SUDELAN
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 | 24000 | 24 | 14640 | 11.616 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 38400 | 8 | 3776 | 10.2564 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 | 32000 | 8 | 3392 | 3.872 | TO MITTAGONG
[11 empty] | 6.893 | 94400 | 40 | 21808 | 25.7444
#2 | 20GP | TO MITTAGONG | FOSCO |  | SUDELAN
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 | 24000 | 24 | 14640 | 11.616 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 38400 | 8 | 3776 | 10.2564 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 | 32000 | 8 | 3392 | 3.872 | TO MITTAGONG
[11 empty] | 6.893 | 94400 | 40 | 21808 | 25.7444
#3 | 20GP | TO MITTAGONG | FOSCO |  | SUDELAN
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 | 24000 | 24 | 14640 | 11.616 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 38400 | 8 | 3776 | 10.2564 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 | 32000 | 8 | 3392 | 3.872 | TO MITTAGONG
[11 empty] | 6.893 | 94400 | 40 | 21808 | 25.7444
#4 | 20GP | TO MITTAGONG | FOSCO |  | SUDELAN
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 | 24000 | 24 | 14640 | 11.616 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 38400 | 8 | 3776 | 10.2564 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 | 31944 | 7.986 | 3386.064 | 3.8652 | TO MITTAGONG
[11 empty] | 6.893 | 94344 | 39.986 | 21802.064 | 25.7376
#5 | 20GP | TO MITTAGONG | FOSCO | TMT
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 720 | 12 | 10884 | 9.2711 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 | 16000 | 16 | 9760 | 7.744 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 38400 | 8 | 3776 | 10.2564 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 6.893 | 55120 | 36 | 24420 | 27.2715
#6 | 20GP | TO MITTAGONG | FOSCO | TMT
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 720 | 12 | 10884 | 9.2711 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 | 15944 | 15.944 | 9725.84 | 7.7169 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 38400 | 8 | 3776 | 10.2564 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 | 0 | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 6.893 | 55064 | 35.944 | 24385.84 | 27.2444
#7 | 20GP | TO MITTAGONG | FOSCO | TMT
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 1260 | 21 | 19047 | 16.2245 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 | 0 | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 20688 | 4.31 | 2034.32 | 5.5256 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 6.893 | 21948 | 25.31 | 21081.32 | 21.7501
#8 | 20GP | TO MITTAGONG | FOSCO | TMT
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 1260 | 21 | 19047 | 16.2245 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 | 18000 | 6 | 5640 | 7.9082 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 6.893 | 19260 | 27 | 24687 | 24.1327
#9 | 20GP | TO MITTAGONG | FOSCO | TMT
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 1260 | 21 | 19047 | 16.2245 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 | 18000 | 6 | 5640 | 7.9082 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 6.893 | 19260 | 27 | 24687 | 24.1327
#10 | 20GP | TO MITTAGONG | FOSCO | TMT
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 1260 | 21 | 19047 | 16.2245 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 | 18000 | 6 | 5640 | 7.9082 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 6.893 | 19260 | 27 | 24687 | 24.1327
#11 | 20GP | TO MITTAGONG | FOSCO | TMT
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 1440 | 24 | 21768 | 18.5422 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 | 9972 | 3.324 | 3124.56 | 4.3811 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 6.893 | 11412 | 27.324 | 24892.56 | 22.9234
#12 | 20GP | TO MITTAGONG |  | TMT
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 1680 | 28 | 25396 | 21.6326 | TO MITTAGONG
| Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 8600 | 814 | 40 | 774 | 0.09 | 1.15 | 0.99 | 1.08 | 1.2296 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 | 0 | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 | 0 | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 6.893 | 1680 | 28 | 25396 | 21.6326
#1 | 20GP | TO MITTAGONG/SITE | FOSCO | TMT | 2024-09-30 | 2024-10-10 | 2024-10-28 | 2024-11-07 |  |  | 2024-11-11
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 120 | 2 | 1814 | 1.5452 | TO MITTAGONG
8952 | Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 2000 | 224 | 30 | 194 | 0.09 | 0.76 | 0.62 | 0.66 | 0.31099 | 26000 | 13 | 2912 | 4.0429 | TO SITE
9258 | Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 4800 | 1 | 472 | 1.2821 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 | 23944 | 5.986 | 1334.878 | 3.6298 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 | 13000 | 13 | 10790 | 9.3122 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 5.9744 | 67864 | 34.986 | 17322.878 | 19.8121
#2 | 20GP | TO SITE | FOSCO | 2024-10-15 | 2024-10-25 | 2024-11-12 | 2024-11-22 |  |  |  | 2024-12-09
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 |  | 0 | 0 | 0 | TO MITTAGONG
8952 | Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 2000 | 224 | 30 | 194 | 0.09 | 0.76 | 0.62 | 0.66 | 0.31099 |  | 0 | 0 | 0 | TO SITE
9258 | Fosco | 165mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 30000 | 6.25 | 2950 | 8.0128 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 | 8000 | 2 | 446 | 1.2128 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 | 13000 | 13 | 10790 | 9.3122 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 5.9744 | 51000 | 21.25 | 14186 | 18.5377
#3 | 20GP | TO SITE | FOSCO | 2024-10-15 | 2024-11-19 | 2024-12-07 | 2024-12-17 |  |  |  | 2025-01-06
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 |  | 0 | 0 | 0 | TO MITTAGONG
8952 | Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 2000 | 224 | 30 | 194 | 0.09 | 0.76 | 0.62 | 0.66 | 0.31099 |  | 0 | 0 | 0 | TO SITE
9258 | Fosco | 165mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 12000 | 2.5 | 1180 | 3.2051 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 | 24000 | 6 | 1338 | 3.6383 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 | 26000 | 26 | 21580 | 18.6243 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 5.9744 | 62000 | 34.5 | 24098 | 25.4677
#4 | 20GP | TO SITE | FOSCO | 2024-10-15 | 2025-01-03 | 2025-01-21 | 2025-01-31 |  |  |  | 2025-02-10
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 |  | 0 | 0 | 0 | TO MITTAGONG
8952 | Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 2000 | 224 | 30 | 194 | 0.09 | 0.76 | 0.62 | 0.66 | 0.31099 | 14000 | 7 | 1568 | 2.1769 | TO SITE
9258 | Fosco | 165mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 6000 | 1.25 | 590 | 1.6026 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 | 24000 | 6 | 1338 | 3.6383 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 | 26000 | 26 | 21580 | 18.6243 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 5.9744 | 70000 | 40.25 | 25076 | 26.0421
#5 | 20GP | TO SITE | FOSCO | 2024-10-15 | 2025-02-14 | 2025-03-04 | 2025-03-14 |  |  |  | 2025-03-24
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 |  | 0 | 0 | 0 | TO MITTAGONG
8952 | Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 2000 | 224 | 30 | 194 | 0.09 | 0.76 | 0.62 | 0.66 | 0.31099 | 14000 | 7 | 1568 | 2.1769 | TO SITE
9258 | Fosco | 165mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 3000 | 0.625 | 295 | 0.80128 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 | 28000 | 7 | 1561 | 4.2446 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 | 26000 | 26 | 21580 | 18.6243 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 5.9744 | 71000 | 40.625 | 25004 | 25.8472
| 20GP | TO SITE | FOSCO | 2024-10-15 | 2025-03-21 | 2025-04-08 | 2025-04-18 |  |  |  | 2025-04-28
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 |  | 0 | 0 | 0 | TO MITTAGONG
8952 | Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 | 3800 | 3.8 | 2318 | 1.8392 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 2000 | 224 | 30 | 194 | 0.09 | 0.76 | 0.62 | 0.66 | 0.31099 | 9972 | 4.986 | 1116.864 | 1.5506 | TO SITE
9258 | Fosco | 165mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 | 6000 | 1.25 | 590 | 1.6026 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 | 20000 | 5 | 1115 | 3.0319 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 | 23944 | 23.944 | 19873.52 | 17.1516 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 5.9744 | 63716 | 38.98 | 25013.384 | 25.1758
| 20GP | TO SITE | FOSCO | 2024-10-15 | 2025-03-21 | 2025-04-08 | 2025-04-18 |  |  |  | 2025-04-28
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 907 | 61 | 846 | 14.1 | 1.025 | 1.005 | 0.75 | 0.77259 | 492 | 8.2 | 7437.4 | 6.3353 | TO MITTAGONG
8952 | Fosco | Screwspike Ss8-150 | 1000 | 610 | 40 | 570 | 0.57 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 940 | 40 | 900 | 0.3 | 1.13 | 1.08 | 1.08 | 1.318 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 2000 | 224 | 30 | 194 | 0.09 | 0.76 | 0.62 | 0.66 | 0.31099 |  | 0 | 0 | 0 | TO SITE
9258 | Fosco | 135mm Dowels | 4800 | 472 | 40 | 432 | 0.09 | 1.11 | 1.1 | 1.05 | 1.2821 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Insulator | 4000 | 223 | 30 | 188 | 0.05 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 40 | 790 | 0.79 | 1.1 | 0.88 | 0.74 | 0.71632 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 372 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 5.9744 | 492 | 8.2 | 7437.4 | 6.3353
Updated Container Configuration
#1 | 20GP | TO MITTAGONG | FOSCO | TMT
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 903 | 57 | 846 | 14.1 | 1.02 | 1 | 0.75 | 0.765 | 660 | 11 | 9933 | 8.415 | TO MITTAGONG
8952 | Fosco | Screwspike Ss8-150 | 1400 | 848 | 50 | 798 | 0.57 | 1.02 | 0.85 | 0.66 | 0.57222 | 11680 | 8.3429 | 7074.7429 | 4.7739 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 990 | 60 | 930 | 0.31 | 1.1 | 1.05 | 1.07 | 1.2359 | 5840 | 1.9467 | 1927.2 | 2.4058 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 2000 | 220 | 40 | 180 | 0.09 | 0.76 | 0.62 | 0.66 | 0.31099 |  | 0 | 0 | 0 | TO SITE
| Fosco | 135mm Dowels | 4800 | 414.8 | 50 | 364.8 | 0.076 | 1.12 | 1.07 | 1.02 | 1.2224 | 23360 | 4.8667 | 2018.6933 | 5.9489 | TO MITTAGONG
| Fosco | Insulator | 4000 | 218 | 30 | 188 | 0.047 | 1.05 | 1.05 | 0.55 | 0.60638 |  | 0 | 0 | 0 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 60 | 800 | 0.8 | 1.06 | 0.87 | 0.74 | 0.68243 |  | 0 | 0 | 0 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 400 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 | 11680 | 2.92 | 1238.08 | 1.4133 | TO MITTAGONG
[11 empty] | 5.8792 | 53220 | 29.0762 | 22191.7162 | 22.9569
#1 | 20GP | TO MITTAGONG | FOSCO | TMT
PO | Supplier | Description | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | Unit Weight | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM | Site
| TMT | RF167 egg baseplate with 2 serrated washers | 60 | 903 | 57 | 846 | 14.1 | 1.02 | 1 | 0.75 | 0.765 | 914 | 15.2333 | 13755.7 | 11.6535 | TO MITTAGONG
8952 | Fosco | Screwspike Ss8-150 | 1400 | 848 | 50 | 798 | 0.57 | 1.02 | 0.85 | 0.66 | 0.57222 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE 3mm Base Pad for RF167 | 3000 | 990 | 60 | 930 | 0.31 | 1.1 | 1.05 | 1.07 | 1.2359 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | HDPE Rail Seat Pad | 2000 | 220 | 40 | 180 | 0.09 | 0.76 | 0.62 | 0.66 | 0.31099 | 5840 | 2.92 | 642.4 | 0.9081 | TO SITE
| Fosco | 135mm Dowels | 4800 | 414.8 | 50 | 364.8 | 0.076 | 1.12 | 1.07 | 1.02 | 1.2224 |  | 0 | 0 | 0 | TO MITTAGONG
| Fosco | Insulator | 4000 | 218 | 30 | 188 | 0.047 | 1.05 | 1.05 | 0.55 | 0.60638 | 11680 | 2.92 | 636.56 | 1.7706 | TO SITE
| Fosco | Rail Clips | 1000 | 830 | 60 | 800 | 0.8 | 1.06 | 0.87 | 0.74 | 0.68243 | 11680 | 11.68 | 9694.4 | 7.9708 | TO SITE
| Sudelan | Fe6 Spring Washer | 4000 | 424 | 40 | 400 | 0.1 | 1.1 | 0.8 | 0.55 | 0.484 |  | 0 | 0 | 0 | TO MITTAGONG
[11 empty] | 5.8792 | 30114 | 32.7533 | 24729.06 | 22.303
Formulas:
N.W. Kg = [Pack Weight]+10
N.W. Kg = [Unit Weight]-10
Unit Weight = [N.W. Kg]+18
Unit Weight = [Volume Cbm]-10-10
L (m) = [Unit Weight]+10
Pack Weight = [G.W. Kg]+10
Pack Weight = [N.W. Kg]-18