## Shipping Schedule Summary
`
[14 empty] | 850 |  | 720 |  | 540 |  | 540 |  | 320
Shipment# | TMT Delivery Date to Lynn | EXW | To Port | ETD | Port | ETA | SHIP OWNER | VESSEL | Nº CONTAINER | BILL LANDING | Assembly or Not | Line | Lot | X8 Thread Rod | Container Qty | EGGX8 Insert | Container Qty | ALT1 RF425 Thread Rod | Container Qty | X8 Check Rail Thread Rod | Container Qty | X8 Check Rail Insert | Container Qty | Container Qty | PORT | Nº DELIVERY NOTE | INVOICE
1 | 2025-04-01 | 2025-04-20 | 2025-04-24 | 2025-04-27 | Shenzhen | 2025-06-06 |  |  |  |  | Assembly | L6 |  |  |  | 2880 | 4 | [6 empty] | 4 | Barcelona
2 | 2025-04-12 | 2025-05-04 | 2025-05-08 | 2025-05-11 | Shenzhen | 2025-06-20 |  |  |  |  | Assembly | L6 |  |  |  | 2880 | 4 | [6 empty] | 4 | Barcelona
3 | 2025-04-22 | 2025-05-18 | 2025-05-22 | 2025-05-25 | Shenzhen | 2025-07-04 |  |  |  |  | Assembly | L6 |  |  |  | 1440 | 2 | [6 empty] | 2 | Barcelona
| 2025-04-22 | 2025-05-18 | 2025-05-22 | 2025-05-25 | Shenzhen | 2025-07-04 |  |  |  |  | Assembly | L6 |  |  |  | 609 | [5 empty] | 96 | 1 | 1 | Barcelona
| 2025-04-22 | 2025-05-18 | 2025-05-22 | 2025-05-25 | Shenzhen | 2025-07-04 |  |  |  |  | Assembly | L6 | [11 empty] | 0 | Barcelona
4 |  | 2025-04-09 | 2025-04-13 | 2025-04-16 | Shanghai | 2025-05-26 |  |  |  |  | Non-Assembly | Metro Madrid | Lot2 |  |  |  |  | 1600 | 3 |  |  |  |  | 3 | Barcelona
5 |  | 2025-05-06 | 2025-05-10 | 2025-05-13 | Shanghai | 2025-06-22 |  |  |  |  | Non-Assembly | L6 |  | 2550 | 3 | [8 empty] | 3 | Barcelona
6 |  | 2025-05-14 | 2025-05-18 | 2025-05-21 | Shanghai | 2025-06-30 |  |  |  |  | Non-Assembly | L6 |  | 1700 | 2 | [8 empty] | 2 | Barcelona
|  | 2025-05-14 | 2025-05-18 | 2025-05-21 | Shanghai | 2025-06-30 |  |  |  |  | Non-Assembly | L6 |  | 403 | [5 empty] | 323 |  |  |  | 0 | Barcelona
[14 empty] | 4653 | 5 | 7809 | 10 | 1600 | 3 | 323 | 0 | 96 | 1 | 19
0
Formulas:
To Port = [EXW]+4
ETD = [To Port]+3
ETA = [ETD]+40
EXW = [EXW, row above]+14

## TMT Schedule
| EGGX8-02 |  |  |  |  | ALT425 |  |  |  | EGGX8-04
| 日产能 | 累积量 | assembly | Non Assembly | balance | 日产能 | 累积量 | Non Assembly | balance | 日产能 | 累积量 | assembly | Non Assembly | balance
2025-03-20 | 280 | 280
2025-03-21 | 280 | 560
2025-03-22 | 280 | 840
2025-03-23 | 0 | 840 | 720 | 0 | 120
2025-03-24 | 280 | 1120
2025-03-25 | 280 | 1400 |  |  |  | 120 | 120
2025-03-26 | 280 | 1680 | 720 | 0 | 240 | 120 | 240
2025-03-27 | 280 | 1960 |  |  |  | 120 | 360
2025-03-28 | 280 | 2240 | 720 | 0 | 80 | 120 | 480
2025-03-29 | 280 | 2520 |  |  |  | 120 | 600 | 540 | 60
2025-03-30 | 0 | 2520 |  |  |  | 0 | 600
2025-03-31 | 280 | 2800 |  |  |  | 120 | 720
2025-04-01 | 280 | 3080 | 720 | 0 | 200 | 120 | 840
2025-04-02 | 280 | 3360 |  |  |  | 120 | 960
2025-04-03 | 280 | 3640 | 720 | 0 | 40 | 120 | 1080 | 540 | 0
2025-04-04 | 280 | 3920 |  |  |  | 120 | 1200
2025-04-05 | 280 | 4200 |  |  |  | 120 | 1320
2025-04-06 | 0 | 4200 |  |  |  | 0 | 1320
2025-04-07 | 280 | 4480 | 720 | 0 | 160 | 120 | 1440
2025-04-08 | 280 | 4760 |  |  |  | 120 | 1560
2025-04-09 | 280 | 5040 | 720 | 0 | 0 | 40 | 1600 | 520 | 0
2025-04-10 | 280 | 5320 | [7 empty] | 60 | 60
2025-04-11 | 280 | 5600 | [7 empty] | 60 | 120
2025-04-12 | 280 | 5880 | 720 | 0 | 120 |  |  |  |  | 60 | 180
2025-04-13 | 0 | 5880 | [7 empty] | 0 | 180
2025-04-14 | 280 | 6160 | [7 empty] | 60 | 240
2025-04-15 | 280 | 6440 | [7 empty] | 60 | 300
2025-04-16 | 280 | 6720 | 720 | 0 | 240 |  |  |  |  | 60 | 360 | 96 | 0 | 264
2025-04-17 | 280 | 7000 | [7 empty] | 59 | 419 | 0 | 323 | 0
2025-04-18 | 280 | 7280 | 720 | 0 | 80
2025-04-19 | 280 | 7560
2025-04-20 | 0 | 7560
2025-04-21 | 280 | 7840
2025-04-22 | 280 | 8120 | 609 | 0 | 311
2025-04-23 | 280 | 8400
2025-04-24 | 280 | 8680 | 0 | 850 | 21
2025-04-25 | 280 | 8960
2025-04-26 | 280 | 9240
2025-04-27 | 0 | 9240
2025-04-28 | 280 | 9520 | 0 | 850 | 11
2025-04-29 | 280 | 9800
2025-04-30 | 142 | 9942
2025-05-05 | 280 | 10222
2025-05-06 | 280 | 10502 | 0 | 403 | 590
2025-05-07 | 280 | 10782
2025-05-08 | 280 | 11062
2025-05-09 | 280 | 11342 | 0 | 850 | 580
2025-05-10 | 280 | 11622
2025-05-11 | 0 | 11622
2025-05-12 | 280 | 11902
2025-05-13 | 280 | 12182 | 0 | 850 | 570
2025-05-14 | 280 | 12462 | 0 | 850 | 0
|  |  | 7809 | 4653 |  |  |  | 1600 |  |  |  | 96 | 323

## Container Config
609+96
Supplier | Description | Qty / Package |  | G.W. Kg | Pack Weight | N.W. Kg | L (m) | W (m) | H (m) | Volume Cbm | Est. Qty | Est. Packages | Est. Weight | Est CBM
TMT | EGGX8 | 36 | 24.1 | 1065.6 | 72 | 900 | 1.165 | 1.01 | 1.125 | 1.3237 | 609 | 16.9167 | 18026.4 | 22.3931
TMT | EGGX8 | 24 |  | 817.2 | 72 | 675 | 1.165 | 1.01 | 0.8 | 0.94132 | 0 | 0 | 0 | 0
TMT | EGGX8 | 18 |  | 536.8 | 40 | 450 | 1.01 | 1.01 | 1.125 | 1.1476 | 0 | 0 | 0 | 0
TMT | EGGX8 | 12 |  | 412.6 | 40 | 337.5 | 1.01 | 1.01 | 0.8 | 0.81608 | 0 | 0 | 0 | 0
TMT | EGGX8x4 | 16 | 48.2 | 1065.6 | 72 | 900 | 1.165 | 1.01 | 1.08 | 1.2708 | 48 | 3 | 3196.8 | 3.8123
TMT | EGGX8x4 | 24 |  | 817.2 | 72 | 675 | 1.165 | 1.01 | 0.8 | 0.94132 | 0 | 0 | 0 | 0
TMT | EGGX8x4 | 18 |  | 536.8 | 40 | 450 | 1.01 | 1.01 | 1.125 | 1.1476 | 0 | 0 | 0 | 0
TMT | EGGX8x4 | 12 |  | 412.6 | 40 | 337.5 | 1.01 | 1.01 | 0.8 | 0.81608 | 0 | 0 | 0 | 0
[11 empty] | 657 | 19.9167 | 21223.2 | 26.2055
Supplier | Description | Unit Net Weight | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM
TMT | EGGx8 | 16.8 | 36 | 609 | 33 | 576 | 0.99 | 0.85 | 0.71 | 0.59747 | 403 | 11.1944 | 6817.4167 | 6.6883
Fosco | SKL12 clip RC13-01 | 0.52 | 1200 | 659 | 35 | 624 | 1 | 0.9 | 0.72 | 0.648 | 806 | 0.67167 | 442.6283 | 0.43524
Fosco | Rail pad RP404 | 0.11 | 2100 | 271 | 40 | 231 | 1.1 | 0.9 | 0.35 | 0.3465 | 403 | 0.1919 | 52.0062 | 0.066495
Fosco | Base pad BP426*10mm | 1.44 | 480 | 751.2 | 60 | 691.2 | 1.05 | 0.96 | 0.95 | 0.9576 | 403 | 0.83958 | 630.695 | 0.80399
Fosco | T-bolt TB22-55 | 0.39 | 1200 | 693.8 | 65 | 468 | 0.93 | 0.88 | 0.79 | 0.64654 | 806 | 0.67167 | 466.0023 | 0.43426
Fosco | Flat washer W6 M22 | 0.05 | 1200 |  |  | 60 |  |  |  |  | 806
Fosco | Nut M22 | 0.084 | 1200 |  |  | 100.8 |  |  |  |  | 806
Sudelan | Threaded Rod Assembly |  | 600 | 720 | 68 | 680 | 1.1 | 0.8 | 0.55 | 0.484 | 806 | 1.3433 | 967.2 | 0.65017
TMT | EGGX8 Guardrail | 32.4 | 20 | 729 | 81 | 648 | 1.08 | 0.9 | 0.7 | 0.6804 | 323 | 16.15 | 11773.35 | 10.9885
Fosco | SKL12 clip RC13-01 | 0.52 | 1200 | 659 | 35 | 624 | 1 | 0.9 | 0.72 | 0.648 | 646 | 0.53833 | 354.7617 | 0.34884
Fosco | Rail pad RP404 | 0.11 | 2100 | 271 | 40 | 231 | 1.1 | 0.9 | 0.35 | 0.3465 | 323 | 0.15381 | 41.6824 | 0.053295
Fosco | Base pad BP7500*10mm | 2.05 | 400 | 880 | 60 | 820 | 1.1 | 0.95 | 0.95 | 0.99275 | 323 | 0.8075 | 710.6 | 0.80165
Fosco | T-bolt TB22-55 | 0.39 | 1200 | 693.8 | 65 | 468 | 0.93 | 0.88 | 0.79 | 0.64654 | 646 | 0.53833 | 373.4957 | 0.34805
Fosco | M22 Flat washer W6 | 0.05 | 1200 |  |  | 60 |  |  |  |  | 646
Fosco | Nut M22 | 0.084 | 1200 |  |  | 100.8 |  |  |  |  | 646
Fosco | Nut M24 | 0.1 | 1200 | 150 | 30 | 120 | 0.9 | 0.8 | 0.35 | 0.252 | 323 | 0.26917 | 40.375 | 0.06783
Fosco | Hex Head Screw 24X110 | 0.539 | 1200 | 686.8 | 40 | 646.8 | 0.96 | 0.84 | 0.65 | 0.52416 | 323 | 0.26917 | 184.8637 | 0.14109
Sudelan | Threaded Rod Assembly |  | 600 | 720 | 68 | 680 | 1.1 | 0.8 | 0.55 | 0.484 | 646 | 1.0767 | 775.2 | 0.52111
Fosco | Spring Washer | 0.045 | 4200 | 363.4 | 40 | 189 | 1.04 | 0.84 | 0.64 | 0.5591 | 323 | 0.076905 | 27.9472 | 0.042998
Fosco | M24 Plain washer | 0.032 | 4200 |  |  | 134.4 |  |  |  |  | 323
[11 empty] | 10730 | 34.7925 | 23658.2241 | 22.3918
Left over
Supplier | Description | Qty / Package |  | G.W. Kg | Pack Weight | N.W. Kg | L (m) | W (m) | H (m) | Volume Cbm | Est. Qty | Est. Packages | Est. Weight | Est CBM
TMT | EGGX8 | 36 | 24.1 | 1065.6 | 72 | 900 | 1.165 | 1.01 | 1.125 | 1.3237 | 0 | 0 | 0 | 0
TMT | EGGX8 | 24 |  | 817.2 | 72 | 675 | 1.165 | 1.01 | 0.8 | 0.94132 | 0 | 0 | 0 | 0
TMT | EGGX8 | 18 |  | 536.8 | 40 | 450 | 1.01 | 1.01 | 1.125 | 1.1476 | 0 | 0 | 0 | 0
TMT | EGGX8 | 12 |  | 412.6 | 40 | 337.5 | 1.01 | 1.01 | 0.8 | 0.81608 | 0 | 0 | 0 | 0
TMT | EGGX8x4 | 16 | 48.2 | 1065.6 | 72 | 900 | 1.165 | 1.01 | 1.08 | 1.2708 | 48 | 3 | 3196.8 | 3.8123
TMT | EGGX8x4 | 24 |  | 817.2 | 72 | 675 | 1.165 | 1.01 | 0.8 | 0.94132 | 0 | 0 | 0 | 0
TMT | EGGX8x4 | 18 |  | 536.8 | 40 | 450 | 1.01 | 1.01 | 1.125 | 1.1476 | 0 | 0 | 0 | 0
TMT | EGGX8x4 | 12 |  | 412.6 | 40 | 337.5 | 1.01 | 1.01 | 0.8 | 0.81608 | 0 | 0 | 0 | 0
[11 empty] | 48 | 3 | 3196.8 | 3.8123