## Shipping Schedule Summary
`
[14 empty] | 900 |  | 720 |  | 540 |  | 540 |  | 320
Shipment# | TMT Delivery Date to Lynn | EXW | To Port | ETD | Port | ETA | SHIP OWNER | VESSEL | Nº CONTAINER | BILL LANDING | Assembly or Not | Line | Lot | X8 Thread Rod | Container Qty | EGGX8 Insert | Container Qty | ALT1 RF425 Thread Rod | Container Qty | X8 Check Rail Thread Rod | Container Qty | X8 Check Rail Insert | Container Qty | Container Qty | PORT | Nº DELIVERY NOTE | INVOICE
1 | 2025-04-01 | 2025-04-20 | 2025-04-24 | 2025-04-27 | Shenzhen | 2025-06-06 |  |  |  |  | Assembly | L6 |  |  |  | 2880 | 4 | [6 empty] | 4 | Barcelona
2 |  | 2025-04-17 | 2025-04-21 | 2025-04-24 | Shanghai | 2025-06-03 |  |  |  |  | Non-Assembly | Metro Madrid | Lot2 |  |  |  |  | 1600 | 3 |  |  |  |  | 3 | Barcelona
3 | 2025-04-12 | 2025-05-04 | 2025-05-08 | 2025-05-11 | Shenzhen | 2025-06-20 |  |  |  |  | Assembly | L6 |  |  |  | 2880 | 4 | [6 empty] | 4 | Barcelona
4 | 2025-04-22 | 2025-05-18 | 2025-05-22 | 2025-05-25 | Shenzhen | 2025-07-04 |  |  |  |  | Assembly | L6 |  |  |  | 1440 | 2 | [6 empty] | 2 | Barcelona
| 2025-04-22 | 2025-05-18 | 2025-05-22 | 2025-05-25 | Shenzhen | 2025-07-04 |  |  |  |  | Assembly | L6 |  |  |  | 609 | [5 empty] | 48 | 1 | 1 | Barcelona
| 2025-04-22 | 2025-05-18 | 2025-05-22 | 2025-05-25 | Shenzhen | 2025-07-04 |  |  |  |  | Assembly | L6 |  | 153 | [5 empty] | 323 |  | 48 | 1 | 1 | Barcelona
5 |  | 2025-05-07 | 2025-05-11 | 2025-05-14 | Shanghai | 2025-06-23 |  |  |  |  | Non-Assembly | L6 |  | 2700 | 3 | [8 empty] | 3 | Barcelona
6 |  | 2025-05-14 | 2025-05-18 | 2025-05-21 | Shanghai | 2025-06-30 |  |  |  |  | Non-Assembly | L6 |  | 1800 | 2 | [8 empty] | 2 | Barcelona
[14 empty] | 4653 | 5 | 7809 | 10 | 1600 | 3 | 323 | 0 | 96 | 2 | 20
0
Formulas:
To Port = [EXW]+4
ETD = [To Port]+3
ETA = [ETD]+40
EXW = [EXW, row above]+14

## Combined Container
609+48
Supplier | Description | Qty / Package |  | G.W. Kg | Pack Weight | N.W. Kg | L (m) | W (m) | H (m) | Volume Cbm | Est. Qty | Est. Packages | Est. Weight | Est CBM
TMT | EGGX8 | 36 | 24.1 | 1065.6 | 72 | 900 | 1.165 | 1.01 | 1.125 | 1.3237 | 609 | 16.9167 | 18026.4 | 22.3931
TMT | EGGX8 | 24 |  | 817.2 | 72 | 675 | 1.165 | 1.01 | 0.8 | 0.94132 | 0 | 0 | 0 | 0
TMT | EGGX8 | 18 |  | 536.8 | 40 | 450 | 1.01 | 1.01 | 1.125 | 1.1476 | 0 | 0 | 0 | 0
TMT | EGGX8 | 12 |  | 412.6 | 40 | 337.5 | 1.01 | 1.01 | 0.8 | 0.81608 | 0 | 0 | 0 | 0
TMT | EGGX8x4 | 16 | 48.2 | 1065.6 | 72 | 900 | 1.165 | 1.01 | 1.08 | 1.2708 | 48 | 3 | 3196.8 | 3.8123
TMT | EGGX8x4 | 24 |  | 817.2 | 72 | 675 | 1.165 | 1.01 | 0.8 | 0.94132 | 0 | 0 | 0 | 0
TMT | EGGX8x4 | 18 |  | 536.8 | 40 | 450 | 1.01 | 1.01 | 1.125 | 1.1476 | 0 | 0 | 0 | 0
TMT | EGGX8x4 | 12 |  | 412.6 | 40 | 337.5 | 1.01 | 1.01 | 0.8 | 0.81608 | 0 | 0 | 0 | 0
[11 empty] | 657 | 19.9167 | 21223.2 | 26.2055
EGG8+EGG8 CK+EGG Assembly
Supplier | Description | Unit Net Weight | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM
TMT | EGGx8 | 16.8 | 36 | 609 | 33 | 576 | 0.98 | 0.88 | 0.7 | 0.60368 | 153 | 4.25 | 2588.25 | 2.5656
Fosco | SKL12 clip RC13-01 | 0.52 | 1250 | 659 | 35 | 650 | 1.04 | 0.97 | 0.58 | 0.5851 | 306 | 0.2448 | 161.3232 | 0.14323
Fosco | Rail pad RP404 | 0.11 | 425 | 708.75 | 50 | 46.75 | 0.97 | 0.95 | 1.03 | 0.94915 | 153 | 0.36 | 255.15 | 0.34169
Fosco | Base pad BP426*10mm | 1.44 | 425 |  |  | 612 |  |  |  |  | 153 | 0.36 | 0 | 0
Fosco | T-bolt TB22-55 | 0.39 | 850 | 510.4 | 65 | 331.5 | 0.88 | 0.8 | 0.7 | 0.4928 | 306 | 0.36 | 183.744 | 0.17741
Fosco | Flat washer W6 M22 | 0.05 | 850 |  |  | 42.5 |  |  |  |  | 306
Fosco | Nut M22 | 0.084 | 850 |  |  | 71.4 |  |  |  |  | 306
Sudelan | Threaded Rod Assembly |  | 600 | 720 | 68 | 680 | 1.1 | 0.8 | 0.55 | 0.484 | 306 | 0.51 | 367.2 | 0.24684
TMT | EGGX8 Guardrail | 32.4 | 20 | 729 | 81 | 648 | 1.08 | 0.9 | 0.7 | 0.6804 | 323 | 16.15 | 11773.35 | 10.9885
Fosco | SKL12 clip RC13-01 | 0.52 | 1250 | 659 | 35 | 650 | 1.04 | 0.97 | 0.58 | 0.5851 | 646 | 0.5168 | 340.5712 | 0.30238
Fosco | Rail pad RP404 | 0.11 | 435 | 979.6 | 40 | 47.85 | 1.01 | 0.95 | 1.09 | 1.0459 | 323 | 0.74253 | 727.3811 | 0.77658
Fosco | Base pad BP7500*10mm | 2.05 | 435 |  |  | 891.75 |  |  |  |  | 323
Fosco | T-bolt TB22-55 | 0.39 | 850 | 510.4 | 65 | 331.5 | 0.88 | 0.8 | 0.7 | 0.4928 | 646 | 0.76 | 387.904 | 0.37453
Fosco | M22 Flat washer W6 | 0.05 | 850 |  |  | 42.5 |  |  |  |  | 646
Fosco | Nut M22 | 0.084 | 850 |  |  | 71.4 |  |  |  |  | 646
Fosco | Nut M24 | 0.1 | 435 | 341.46 | 30 | 43.5 | 0.88 | 0.8 | 0.7 | 0.4928 | 323 | 0.74253 | 253.5439 | 0.36592
Fosco | Hex Head Screw 24X110 | 0.539 | 435 |  |  | 234.465 |  |  |  |  | 323
Fosco | Spring Washer | 0.045 | 435 |  |  | 19.575 |  |  |  |  | 323
Fosco | M24 Plain washer | 0.032 | 435 |  |  | 13.92 |  |  |  |  | 323
Sudelan | Threaded Rod Assembly |  | 600 | 720 | 68 | 680 | 1.1 | 0.8 | 0.55 | 0.484 | 646 | 1.0767 | 775.2 | 0.52111
TMT | EGGX8x4 | 16 | 48.2 | 1065.6 | 72 | 900 | 1.165 | 1.01 | 1.08 | 1.2708 | 48 | 3 | 3196.8 | 3.8123
[11 empty] | 7528 | 29.0733 | 21010.4174 | 20.6161

## EGG8 Thread Rod
EGG8 900
Supplier | Description | Unit Net Weight | Qty / Package | G.W. Kg | Pack Weight | N.W. Kg | L (m) | W (m) | H (m) | Volume Cbm | CONTRACT QTY | Est. Packages | Est. Weight | Est CBM
TMT | EGGx8 | 16.8 | 36 | 637.8 | 33 | 604.8 | 0.98 | 0.88 | 0.7 | 0.60368 | 900 | 25 | 15945 | 15.092
TMT | EGGx8 | 16.8 | 22 | 402.6 | 33 | 369.6 | 0.98 | 0.88 | 0.55 | 0.47432 | 0 | 0 | 0 | 0
Fosco | SKL12 clip RC13-01 | 0.52 | 1250 | 659 | 35 | 650 | 1.04 | 0.97 | 0.58 | 0.5851 | 1250 | 1 | 659 | 0.5851
Fosco | SKL12 clip RC13-01 | 0.52 | 550 | 659 | 35 | 286 | 1.04 | 0.97 | 0.58 | 0.5851 | 550 | 1 | 659 | 0.5851
Fosco | Rail pad RP404 | 0.11 | 450 | 747.5 | 50 | 49.5 | 0.97 | 0.95 | 1.08 | 0.99522 | 900 | 2 | 1495 | 1.9904
Fosco | Base pad BP426*10mm | 1.44 | 450 |  |  | 648 |  |  |  |  | 900
Fosco | T-bolt TB22-55 | 0.39 | 900 | 536.6 | 65 | 351 | 0.88 | 0.8 | 0.75 | 0.528 | 1800 | 2 | 1073.2 | 1.056
Fosco | Flat washer W6 M22 | 0.05 | 900 |  |  | 45 |  |  |  |  | 1800
Fosco | Nut M22 | 0.084 | 900 |  |  | 75.6 |  |  |  |  | 1800
Sudelan | Threaded Rod Assembly |  | 600 | 720 | 68 | 680 | 1.1 | 0.8 | 0.55 | 0.484 | 1800 | 3 | 2160 | 1.452
[11 empty] | 11700 | 34 | 21991.2 | 20.7606